## Sheet1
Priority Area | Blueprint Function | Executive Lead | Non Executive Lead | Operational Lead | Objective | Specific Actions | Timeline | Status | Intended Good Governance Outcome
Performance | Holding to Account, Assurance Framework | Deputy Chief Executive | Chair FRP Committee | Head of Strategy & Transformation Directorates and operational units | Performance reporting to triangulate with other NHS Highland data, including patient experience, and use trajectories, trends and benchmarking with other Boards & systems, | Data in IPQR to include wider in-house data to assist with triangulation and to refer to any live critical issues facing NHS Highland. IPQR also to include description of trends, trajectories and benchmark with other Boards. | 2023-12-31 |  | Better understanding of whole system performance, improved scrutiny of data and enhanced holding to account of Executives. Improvement to assurance at Board level and create opportunity for 'deep dives' where necessary. Provide opportunity to triangulate data with external reports and benchmarking information. Better oversight and consistency of system-wide assurance at Board level. Greater clarity of expectation and understanding where progress is not being made.
|  | Deputy Chief Executive | Chair FRP Committee | Head of Strategy & Transformation Directorates and operational units | IPQR to make explicit linkage with quality of care and outcomes. | Incorporate patient experience into IPQR with explicit reference to care and outcomes. | 2024-07-31 |  | Better responsiveness to the rights and interests of patients and stakeholders in the healthcare system. Development of trust and increase public confidence in the organisation as a public body.
Finance & Best Value | Setting Direction, Assurance Framework | Director of Finance, Deputy Chief Executive | Chair FRP Committee |  | Creation of a framework for business change/service redesign to evidence the value of expenditure with links to ADP & finance. | Review proforma for approval of business cases, evolve a checklist to ensure good decisions and best value for the wider organisation. Best Value to be based on Realistic Medicine definition. | 2023-12-31 |  | Improved and better evidenced and assured decisions on investment/disinvestment in delivery of services. Improvements in forward planning, horizon scanning and awareness of associated risks. Improvements in connection and professional advice from ACF and APF. Better contribution from ACF and APF in terms of shaping policy and strengthening their voice at the Board.
|  | Director of Finance and | ACF and APF stakeholder members | Board Secretary | Advisory Boards to inform and be part of the decision making process for business change. | Hold a development session and engage with APF and ACF to initiate improvements in co-production, engagement and involvement with business change processes and governance. | 2023-12-31 |  | Board members gain a fuller picture of the issues, risks and opportunities facing the organisation. Board members thinking and decisions are informed by issues affecting the workforce and benefit from the advice from clinical colleagues on issues that could affect clinical practice and employee relations. Assists the Board in discussions with other key stakeholders.
Risk | Risk, Assurance Framework | Medical Director | Chair Audit Committee |  | Board to reset its Risk Appetite | Board to refine the risk framework and refine the risk appetite statement in consultation with clinicians - to be brought back to a Board Development Session withn 2023-24 | 2023-12-31 | Partially Complete | A more active approach to governance to make more timely, well informed and strategic decisions. Better skills in identifying, escalating and managing issues. Evidence of staff being empowered to manage risk with a clearer understanding of the Board's risk appetite and tolerance being evident at Committee and Board level. Board to get assurance on the same approach to risk being followed throughout the organisation. Clearer focus on horizon scanning being evident through SBARs to Committees and the Board.
|  | Medical Director | Chair Audit Committee |  | Translation of revised risk appetite into workable processes for colleagues | Review and revise organisational controls in line with revised risk appetite. | 2024-07-31 |  | Improved alignment of organisation's operations with the wider strategic and policy context.
|  | Medical Director | Chair Audit Committee |  | Upskilling workforce in risk management knowledge and methodology | Devise and cascade organisational training to support and empower colleagues to take appropriate decisions flowing from the revised risk appetite. | 2024-07-31 |  | Colleagues are better informed to rapidly identify, escalate and manage issues which might otherwise not have been identified.
|  | Director of Finance | Chair Audit Committee | Board Secretary | Audit Committee to include oversight of the risk process within its ToR | This is already in place. | 2023-12-31 | Complete
Culture | Influencing Culture | Chief Executive and Executive Team | Employee Director and Chair Staff Governance Committee | Directorates & senior managers, Head of OD | Clear thread of organisational culture/ethos between front line teams and the Board. Ensure a broader systemic overview of the organisation's ethos incorporating quality, safety and practitioner outcomes with links to the performance framework. Clarity of how this is reflected in the work of governance committees with distinct reference within SBARs. | Fulfilment of the intentions of the ADP for People and Culture. | 2023-12-31 |  | Improved alignment of organisation's operations with the wider strategic and policy context. Organisation's values being evident at Board and Committee level through SBARs and delivery of Staff Governance Standard
|  | Chief Executive and Executive Team | Employee Director and Chair Staff Governance Committee | Directorates & senior managers, Head of OD | Reframe and transition of the organisational culture/ethos with emphasis on learning and development throughout the performance framework. | Paper to Staff Governance Committee in September 2023 and initiation of the following: • Focus on developing confidence and capability of management colleagues through a review of the leadership and management programmes • Head of OD to draft a localised proposal on an established nationwide approach to assist colleagues to address staffing matters outwith formal processes and build a proposal over next 3-5 years • Training in compassionate leadership and embrace ‘Civility’ work undertaken by Helen Freeman, with colleague engagement and input • Reestablishment and refresh of Partnership working to maximise the reach of the Area Partnership Forum in terms of employee engagement • Revision of People Processes • Culture Oversight Group to be re-instated | 2023-12-31 |  | Values being shared throughout the organisation about how things are done, how decisions are made, how people interact and work is carried out. Board actively involved in determining, demonstrating and promoting shared values and ethos. Organisation's values being evident at Board and Committee level through SBARs and delivery of Staff Governance Standard
|  | Director of People and Culture | Employee Director and Chair Staff Governance Committee | Head of Comms and Engagement | Ensure engagement and communication with staff fits within the governance structure | Clarify where staff engagement sits within People and Culture. Clarify permanent ongoing resource and expectations. Establish appropriate process for reporting. Compliance with Staff Governance Standard through Staff Governance Committee and in collaboration with Area Partnership Forum on a yearly basis. | 2023-12-31 |  | Improvements in respecting and pursuing the rights and views of staff. Clarity of communication of the organisation's purpose, aims, values, objectives, priorities and targets. Improvement to upholding the Staff Governance Standards.
Quality of Care | Evaluation and Review | Nurse Director Medical Director | Chair Clinical Governance Committee |  | Establish and agree a plan to implement a Quality Framework arising from recent work undertaken with Amanda Croft. | Establish a clear definition, understanding and organisational prioritisation of quality that is underpinned by patient and colleague experience, and National Guidelines. | 2024-07-31 |  | A clear link between quality, patient experience and outcomes being evident throughout the organisation and at Committee/Board level. Establishment of a Quality Framework that embeds culture improvement and quality of workplace experience. Quality outcomes triangulate with care opinion.
|  | Nurse Director Medical Director | Chair Clinical Governance Committee |  | Ensure that patient feedback is consistently collected, effectively shared, responded to and utilised across all areas of the Board. | Ensure systems and processes are developed to improve in the collection, reporting and use of patient experience feedback across the Board | 2024-07-31 |  | A consistent mechanism to receive patient feedback, to celebrate good practice, learn and improve patient experience.
Board Member development | Setting Direction, Evaluation and Review, Diversity, Skills & Experience | Director of People and Culture | Board Chair | Board Secretary | Training for members to enhance skills in challenge and scrutiny, particularly relating to how the board works effectively in the strategic areas. | Non Exec training plan to be developed to address training needs identified from Non Executive appraisals and succession plan. A workshop to be held to understand the current skill-sets and skills gap, particularly relating to scrutiny and challenge. Further training to be arranged to meet any skills gaps. | 2023-12-31 | Partially Complete | Board members equipped to ask appropriate questions, constructively challenge and scrutinise data to be evidenced at Committee meetings and captured within minutes. Improvement in Board member understanding of the Strategy's alignment with quality improvement.
SBAR Development | Evaluation and Review | Executive Team | Board and Committee Chairs | Board Secretary | Improvements to SBAR contents with clear evidence of assurance being offered to improve the Board's assurance and scrutiny role. | Report writers to record how to lift assurance to substantial within SBAR format. Further training and guidance to report authors. | 2023-12-31 | Partially Complete | Clear and consise SBARs to Board and Committee meetings with well evidenced assurance, risks, mitigations, options appraisals. Active use of the Board's agreed Assurance Matrix at Committee and Boad meetings - assurance levels agreed to refer to the appropriate actions available to Committees and Board
|  | Executive Team | Board and Committee Chairs | Board Secretary | Improvements to use of assurance maturity matrix within Committee and Board meetings | Committee Chairs to use the assurance matrix to retain better oversight of business that has less than substantial assurance. Chairs to ensure Committees take an active and deliberate focus on the level of assurance during agenda preparation and during Committee meetings. | 2023-12-31 |  | An Active approach to delivering good governance with Board and Committees considering the right things, the right evidence and use the tools to bring about the best response.
Engagement | Engaging Stakeholders, Influencing Culture, Evaluation and Review | Director of People & Culture, Medical Director, Chief Officer Community, | Chairs Clinical Governance Committee and Highland Health and Social Care Committee | Head of Comms & Engagement | Embedding patient and community representation and feedback within the performance framework and governance structure | Pilot increased publicity of Care Opinion Pilot in Community services and decision made on whether or not to expand Care Opinion to Community services Report on learnings from pilots to HHSCC and CGC in November as part of Community Engagement reporting and capture Highland HSCP assessment of the Engagement Framework's progress as part of this. Continue Highland 100 panel recruitment - ongoing to end of 2023/24 - and send out first survey by December 2023 | 2023-12-31 |  | • Learning from Care Opinion to inform whether this is a suitable mechanism for board-wide service user experience reporting • Baseline of experience/perceptions from Highland 100 panel • Panel in place to provide a sounding board for services