## Master Sheet
Priority Area | Date of Committee Meeting | Blueprint Function | Executive Lead | Non Executive Lead | Operational Lead | Objective | Specific Actions | Timeline | Status | Intended Good Governance Outcome | Status Update One | Status Update Two | Update for July 2024 Board meeting
Performance | FRP - 3 November 2023 and 3 May 2024 | Holding to Account, Assurance Framework | Deputy Chief Executive | Chair FRP Committee | Head of Strategy & Transformation Directorates and operational units | Performance reporting to triangulate with other NHS Highland data, including patient experience, and use trajectories, trends and benchmarking with other Boards & systems, | Data in IPQR to include wider in-house data to assist with triangulation and to refer to any live critical issues facing NHS Highland. IPQR also to include description of trends, trajectories and benchmark with other Boards. | 2023-12-31 |  | Better understanding of whole system performance, improved scrutiny of data and enhanced holding to account of Executives. Improvement to assurance at Board level and create opportunity for 'deep dives' where necessary. Provide opportunity to triangulate data with external reports and benchmarking information. Better oversight and consistency of system-wide assurance at Board level. Greater clarity of expectation and understanding where progress is not being made. | Lorraine Cowie 21/12/23 - All data now has national benchmarking and a clearer description of progress made and work still to complete with timescales. All areas have trajectories where agreed and once integrated service planning is complete this will improve further. Benchmarking is available on all pages of IPR. | Lorraine Cowie 16/04/24: From my perspective the IPQR ask is complete for the moment. IPQR will always evolve and how we give assurance will be an ongoing process. | Lorraine Cowie 13/06/2024 - confirmed no further update and remained complete
| FRP - 3 November 2023 and 3 May 2024 |  | Deputy Chief Executive | Chair FRP Committee | Head of Strategy & Transformation Directorates and operational units | IPQR to make explicit linkage with quality of care and outcomes. | Incorporate patient experience into IPQR with explicit reference to care and outcomes. | 2024-07-31 |  | Better responsiveness to the rights and interests of patients and stakeholders in the healthcare system. Development of trust and increase public confidence in the organisation as a public body. | Lorraine Cowie 21/12/2023 Head of Strategy and Transformation has agreed a test of change to be used for the March FRP Committee IPQR relating to cancer and radiology where care opinion and QPIs are embedded. This pilot will be reviewed to expand to other areas once the test of change has been approved. | Lorraine Cowie 16/04/24: From my perspective the IPQR ask is complete for the moment. IPQR will always evolve and how we give assurance will be an ongoing process. | Lorraine Cowie 13/06/2024 - confirmed no further update and remained complete.
Finance & Best Value | FRP - 3 November 2023 and 3 May 2024 | Setting Direction, Assurance Framework | Director of Finance, Deputy Chief Executive | Chair FRP Committee |  | Creation of a framework for business change/service redesign to evidence the value of expenditure with links to ADP & finance. | Review proforma for approval of business cases, evolve a checklist to ensure good decisions and best value for the wider organisation. Best Value to be based on Realistic Medicine definition. | 2023-12-31 |  | Improved and better evidenced and assured decisions on investment/disinvestment in delivery of services. Improvements in forward planning, horizon scanning and awareness of associated risks. Improvements in connection and professional advice from ACF and APF. Better contribution from ACF and APF in terms of shaping policy and strengthening their voice at the Board. | Heledd Cooper 09/10/2023 Still a work in progress and the intention is to align the financial planning, performance and workforce planning for 24/25 budget setting. Heledd is working on a document to set this out. Lorraine Cowie 21/12/23 New Integrated Service Planning and the ADP guidance has set this out and will create a baseline for redesign. Realistic medicine has a clear project plan and is part of the strategy & transformation team. 15 box model produced by SG has a clear improvement plan developed and approved by EDG. | Heledd Cooper 24.06.2024: All of these actions have been completed. The business case proforma was the last item and this is complete and is being tested through the eHealth team for the EPR business case. Budget setting manual was completed and Integrated service planning in place. Best value documentation is being compiled. Lorraine Cowie 16/04/2024: now complete and has been reflected in process given to Board development and in the ADP/MTP. Board development time undertaken with ACF colleagues. | Lorraine Cowie 13/06/2024 - confirmed no further update and remained complete. Heledd Cooper 24.06.2024: All of these actions have been completed. The business case proforma was the last item and this is complete and is being tested through the eHealth team for the EPR business case.
| FRP - 5 January 2024 and 3 May 2024 |  | Director of Finance and | ACF and APF stakeholder members | Board Secretary | Advisory Boards to inform and be part of the decision making process for business change. | Hold a development session and engage with APF and ACF to initiate improvements in co-production, engagement and involvement with business change processes and governance. | 2023-12-31 |  | Board members gain a fuller picture of the issues, risks and opportunities facing the organisation. Board members thinking and decisions are informed by issues affecting the workforce and benefit from the advice from clinical colleagues on issues that could affect clinical practice and employee relations. Assists the Board in discussions with other key stakeholders. | ACF and APF will hold discussions at their January & February 2024 meetings on ‘Processes for business change – Advisory Board engagement’ covering staffing, Performance, Planning and Finance | Complete APF and ACF meetings in April and May have both considered their the annual delivery plan and the Financial plan and how the respective forums can contribute to business change.
Risk | September Board Development Session | Risk, Assurance Framework | Medical Director | Chair Audit Committee |  | Board to reset its Risk Appetite | Board to refine the risk framework and refine the risk appetite statement in consultation with clinicians - to be brought back to a Board Development Session withn 2023-24 | 2023-12-31 | Partially Complete | A more active approach to governance to make more timely, well informed and strategic decisions. Better skills in identifying, escalating and managing issues. Evidence of staff being empowered to manage risk with a clearer understanding of the Board's risk appetite and tolerance being evident at Committee and Board level. Board to get assurance on the same approach to risk being followed throughout the organisation. Clearer focus on horizon scanning being evident through SBARs to Committees and the Board. | Boyd Peters The Board Risk Appetite was agreed by the Board in November 2023. The next phase (using the risk appetite within the strategic and operational parts of NHS Highland) will occur throughout 2024. |  | Boyd Peters 25.06.2024 - complete - A session for the exec directors is planned now, late July.
| 6 February 2024 and 21 May 2024 |  | Medical Director | Chair Audit Committee |  | Translation of revised risk appetite into workable processes for colleagues | Review and revise organisational controls in line with revised risk appetite. | 2024-07-31 |  | Improved alignment of organisation's operations with the wider strategic and policy context. | Boyd Peters 28/09/2023 - Will occur during 2024 | Boyd Peters 09/05/2024 - The timeline for this will run to the end of 2024, with no further update from the last Board Development session. The next step will be an exec director in group discussion, which is still awaited. No staff resource has been allocated to deliver the work, therefore, it will require action from the exec team.Expects the Exec Director Group to have further input. | Boyd Peters 25.06.2024 - No change to the comments previously given.
| 6 February 2024 and 21 May 2024 |  | Medical Director | Chair Audit Committee |  | Upskilling workforce in risk management knowledge and methodology | Devise and cascade organisational training to support and empower colleagues to take appropriate decisions flowing from the revised risk appetite. | 2024-07-31 |  | Colleagues are better informed to rapidly identify, escalate and manage issues which might otherwise not have been identified. | Boyd Peters 28/09/2023 Will occur during 2024 | Boyd Peters 09/05/2024 - The timeline for this will run to the end of 2024, with no further update from the last Board Development session. The next step will be an exec director in group discussion, which is still awaited. No staff resource has been allocated to deliver the work, therefore, it will require action from the exec team.Expects the Exec Director Group to have further input. | Boyd Peters 25.06.2024 - No change to the comments previously given.
| COMPLETED |  | Director of Finance | Chair Audit Committee | Board Secretary | Audit Committee to include oversight of the risk process within its ToR | This is already in place. | 2023-12-31 | Complete |  | Complete | Complete | Complete
Culture | Staff Governance 8 November 2023 and 7 May 2024 | Influencing Culture | Chief Executive and Executive Team | Employee Director and Chair Staff Governance Committee | Directorates & senior managers, Head of OD | Clear thread of organisational culture/ethos between front line teams and the Board. Ensure a broader systemic overview of the organisation's ethos incorporating quality, safety and practitioner outcomes with links to the performance framework. Clarity of how this is reflected in the work of governance committees with distinct reference within SBARs. | Fulfilment of the intentions of the ADP for People and Culture. | 2023-12-31 |  | Improved alignment of organisation's operations with the wider strategic and policy context. Organisation's values being evident at Board and Committee level through SBARs and delivery of Staff Governance Standard | Gareth Adkins 06/09/2023 A refreshed leadership and culture framework has been discussed with the Cultural oversight group including proposals to strengthen our approach to leadership development and a learning system to support wider engagement with our staff and our leaders in practising compassionate care. This has also progressed through the area partnership forum, staff governance committee and an update provided to the board. The medical and nurse director are progressing discussions with stakeholders in relation to the externally commissioned review of our approach to quality. This will develop consensus on next steps for evolving our approach to quality. Gareth Adkins confirmed on 05/10/2023 and 11/12/2023 that there was no further updates as of yet. | Gareth Adkins 11/04/2024 Culture Oversight Group continues to oversee delivery of the leadership and culture framework. Good progress against framework with refreshed leadership development programme launched on time and new staff engagement programme developed and to be progressed in 24/25. A Further area of development planned and agreed by COG is a review of our approach to using qualitative and quantitative data to assess quality and performance across the organisation. This will need to include a holistic approach to reviewing and using data across clinical, financial, performance and staff governance domains of quality. This would enable identification of services or teams who are struggling and assessment of support required to develop leadership and team effectiveness for improvements in quality including team culture. In addition we have agreed to explore what more we need to do to support teams working in small communities Once we have developed and embedded these 4 elements of our leadership and culture framework we would transition to business as usual with staff governance committee receiving assurance we have a mechanism for identifying opportunities for improvement in quality and culture through effective use of qualitative and quantitative data and we can support services and teams with improvement. | Gareth Adkins 25/06/2024 - Phase 1 of the Leadership and Culture programme is complete with refreshed leadership development programme in place. Phase 2 has commenced with a focus on developing our learning system and considering cohort training for key groups of managers. Staff Engagement work is progressing and will be reported on late in 2024-2025 COG has agreed to setting up short life working group to development quality assurance framework to identify teams that are struggling in one or more dimensions of quality including leadership, assessing their strengths and weaknesses and developing an appropriate action/intervention plan - this plan would be based on 5 levels of intervention including level 5 - no action required level 4 no intervention but local action plan required (no monitoring) level 3 minimal intervention with local action plan required with external monitoring level 2 - significant intervention with board level action plan and monitoring level 1 - direct management intervention with board level action plan and monitoring This will work will include consideration of teams in small communities Further work is also planned with staff governance committee, local area partnership forums, staffside and senior managers to complete development sessions on partnership working during 2024-2025
| Staff Governance 8 November and 7 May 2024 |  | Chief Executive and Executive Team | Employee Director and Chair Staff Governance Committee | Directorates & senior managers, Head of OD | Reframe and transition of the organisational culture/ethos with emphasis on learning and development throughout the performance framework. | Paper to Staff Governance Committee in September 2023 and initiation of the following: • Focus on developing confidence and capability of management colleagues through a review of the leadership and management programmes • Head of OD to draft a localised proposal on an established nationwide approach to assist colleagues to address staffing matters outwith formal processes and build a proposal over next 3-5 years • Training in compassionate leadership and embrace ‘Civility’ work undertaken by Helen Freeman, with colleague engagement and input • Reestablishment and refresh of Partnership working to maximise the reach of the Area Partnership Forum in terms of employee engagement • Revision of People Processes • Culture Oversight Group to be re-instated | 2023-12-31 |  | Values being shared throughout the organisation about how things are done, how decisions are made, how people interact and work is carried out. Board actively involved in determining, demonstrating and promoting shared values and ethos. Organisation's values being evident at Board and Committee level through SBARs and delivery of Staff Governance Standard | Gareth Adkins 06/09/2023 Cultural oversight group terms of reference reviewed and group re-established and refreshed. A refreshed leadership and culture framework has been discussed with the Cultural oversight group including proposals to strengthen our approach to leadership development and a learning system to support wider engagement with our staff and our leaders in practising compassionate care. This has also progressed through the area partnership forum, staff governance committee and an update provided to the board. A programme of improvement has been established focussed on key people processes starting with recruitment. Further workstreams to be added on payroll and job evaluation Significant work already undertaken to enhance awareness and understanding of partnership working. Gareth Adkins confirmed on 05/10/2023 and 11/12/2023 that there was no further updates as of yet. | Gareth Adkins 11/04/24 Culture Oversight Group continues to oversee delivery of the leadership and culture framework. Good progress against framework with refreshed leadership development programme launched on time and new staff engagement programme developed. Structured approach to improving statutory and mandatory training underway and appraisal compliance improvement plan approved by area partnership forum and Staff governance committee. Further work on partnership working planned for 24/25 including development session for APF and Staff Governance committee. | Gareth Adkins 25/06/2024 - People and Culture Portfolio board established and regular reporting to area partnership forum and staff governance committee. Work progressing well.
| Staff Governance 8 November and 7 May 2024 |  | Director of People and Culture | Employee Director and Chair Staff Governance Committee | Head of Comms and Engagement | Ensure engagement and communication with staff fits within the governance structure | Clarify where staff engagement sits within People and Culture. Clarify permanent ongoing resource and expectations. Establish appropriate process for reporting. Compliance with Staff Governance Standard through Staff Governance Committee and in collaboration with Area Partnership Forum on a yearly basis. | 2023-12-31 |  | Improvements in respecting and pursuing the rights and views of staff. Clarity of communication of the organisation's purpose, aims, values, objectives, priorities and targets. Improvement to upholding the Staff Governance Standards. | Gareth Adkins 06/09/2023 Proposal being developed on staff engagement approach building on work already undertaken to establish new methods such as listening and learning panels. Gareth Adkins confirmed on 05/10/2023 and 11/12/2023 that there was no further updates. | Gareth Adkins 11/04/24 Culture Oversight Group continues to oversee delivery of the leadership and culture framework. Good progress against framework with refreshed leadership development programme launched on time and new staff engagement programme developed and to be progressed in 24/25. The staff engagement programme will link with imatter and other sources of feedback to explore staff opinions and develop organisational actions through focus groups. | Gareth Adkins 25/06/2024 - work ongoing and progressing well
Quality of Care | CGC 7 March 2024 and 2 May 2024 HHSC 6 March 2024 and 8 May 2024 | Evaluation and Review | Nurse Director Medical Director | Chair Clinical Governance Committee |  | Establish and agree a plan to implement a Quality Framework arising from recent work undertaken with Amanda Croft. | Establish a clear definition, understanding and organisational prioritisation of quality that is underpinned by patient and colleague experience, and National Guidelines. | 2024-07-31 |  | A clear link between quality, patient experience and outcomes being evident throughout the organisation and at Committee/Board level. Establishment of a Quality Framework that embeds culture improvement and quality of workplace experience. Quality outcomes triangulate with care opinion. | Louise Bussell - 15/09/2023 The outcome of the Quality review has been presented and discussed at the Area Clinical Forum, the Area Medical Committee, NMAHP Advisory Group, Psychology Leads group, and the Area Pharmacy Committee as part of the development of a consensus on a Quality Framework. April 2024 Board Briefing session planned to focus exclusively on the quality framework and to include Area Clinical Forum colleagues to explore improvements in the Board and ACF's joint working arrangements. | Louise Bussell 12/04/2024 A joint development session between ACF and the Board was held on 23rd April 2024 focussing on the proposed quality framework to consider if it is the best fit for the work required | Louise Bussell and Boyd Peters 27.06.24 - The quality work to date and a proposed quality framework were presented and explored at the joint ACF and Board in April. The feedback from the session has helped shape the direction of our quality work. We have since had a session in May with clinical leaders in relation to this work and its relationship to clinical governance. We are now reviewing how we are already working across the Board prior to introducing the framework to ensure we are in a position to do this in a planned and measured way. The quality framework will be closely related to this work as patient feedback and experience is part of the rounded picture captured within the framework dataset. We have commenced a mapping exercise to understand where we are capturing patient experience effectively already, where we need to do more and where we do not have a route for feedback other than through formal processes such as complaints. This includes our position in relation to patient opinion. We are also exploring what approaches other Boards have taken.
| CGC 7 March 2024 and 2 May 2024 HHSC 6 March 2024 and 8 May 2024 |  | Nurse Director Medical Director | Chair Clinical Governance Committee |  | Ensure that patient feedback is consistently collected, effectively shared, responded to and utilised across all areas of the Board. | Ensure systems and processes are developed to improve in the collection, reporting and use of patient experience feedback across the Board | 2024-07-31 |  | A consistent mechanism to receive patient feedback, to celebrate good practice, learn and improve patient experience. | Louise Bussell - 15/09/2023 Exploring approaches being utilised internally and externally in order to put forward recommendations for establishing consistent patient feedback. | Louise Bussell 12/04/2025 This is going to be a longer term action as it requires considerable development work. Currently mapping out board position in order to establish a plan | Boyd Peters 25/06/2024 - no change to report
Board Member development | Board Chairs |  | Director of People and Culture | Board Chair | Board Secretary | Training for members to enhance skills in challenge and scrutiny, particularly relating to how the board works effectively in the strategic areas. | Non Exec training plan to be developed to address training needs identified from Non Executive appraisals and succession plan. A workshop to be held to understand the current skill-sets and skills gap, particularly relating to scrutiny and challenge. Further training to be arranged to meet any skills gaps. | 2023-12-31 | Partially Complete | Board members equipped to ask appropriate questions, constructively challenge and scrutinise data to be evidenced at Committee meetings and captured within minutes. Improvement in Board member understanding of the Strategy's alignment with quality improvement. | Ruth Daly - Discussions held with NES colleagues to deliver bespoke training for Board members using current reports and scenario workshops. Detailed programme for the session currently being prepared and the date of the session stil to be agreed | Complete - Making Data Count workshop held with Board members, with follow-up sessions to be organised by NES being discussed | Complete
SBAR Development | Board Chairs | Evaluation and Review | Executive Team | Board and Committee Chairs | Board Secretary | Improvements to SBAR contents with clear evidence of assurance being offered to improve the Board's assurance and scrutiny role. | Report writers to record how to lift assurance to substantial within SBAR format. Further training and guidance to report authors. | 2023-12-31 | Partially Complete | Clear and consise SBARs to Board and Committee meetings with well evidenced assurance, risks, mitigations, options appraisals. Active use of the Board's agreed Assurance Matrix at Committee and Boad meetings - assurance levels agreed to refer to the appropriate actions available to Committees and Board | Ruth Daly - Improvements to demonstrating how to lift assurance levels now being made with report writers, and updates to training materials for report writers has taken place. Additional sessions for report writers planned to take place before the end of 2023. | Complete - Board Secretary has delivered training to report writers during April and May 2024 focussing on good practice guidance, the assurance matrix and the feedback from Board and Governance Committees throughout the self evaluation exercises.Whle this action has been deemed to be complete, it represents an ongoing piece of work to support the boards information assurance framework. | Complete
| Board Chairs |  | Executive Team | Board and Committee Chairs | Board Secretary | Improvements to use of assurance maturity matrix within Committee and Board meetings | Committee Chairs to use the assurance matrix to retain better oversight of business that has less than substantial assurance. Chairs to ensure Committees take an active and deliberate focus on the level of assurance during agenda preparation and during Committee meetings. | 2023-12-31 |  | An Active approach to delivering good governance with Board and Committees considering the right things, the right evidence and use the tools to bring about the best response. | Ruth Daly - Committee Chairs have discussed the use of the assurance matrix at the Chairs' group. | Complete - further discussions held with Board Chairs on guiding committees to address the level of assurance taken at meetings. | Complete
Engagement | CGC 2 November 2023 and 2 May 2024 HHSC 1 November 2023 and 2 May 2024 | Engaging Stakeholders, Influencing Culture, Evaluation and Review | Director of People & Culture, Medical Director, Chief Officer Community, | Chairs Clinical Governance Committee and Highland Health and Social Care Committee | Head of Comms & Engagement | Embedding patient and community representation and feedback within the performance framework and governance structure | Pilot increased publicity of Care Opinion Pilot in Community services and decision made on whether or not to expand Care Opinion to Community services Report on learnings from pilots to HHSCC and CGC in November as part of Community Engagement reporting and capture Highland HSCP assessment of the Engagement Framework's progress as part of this. Continue Highland 100 panel recruitment - ongoing to end of 2023/24 - and send out first survey by December 2023 | 2023-12-31 |  | • Learning from Care Opinion to inform whether this is a suitable mechanism for board-wide service user experience reporting • Baseline of experience/perceptions from Highland 100 panel • Panel in place to provide a sounding board for services | Ruth Fry - 15/09/2023 Pilots going well with measurable increase in stories being received and responded to. New services seeking to join the pilot. Work ongoing between Strategy and Transformation and Communications and Engagement teams to embed engagement and feedback into planning and redesign protocols. HHSCC and CGC report drafted. Highland 100 panel contact details being collated and first survey drafted. Ruth Fry - 11/12/2023 Care Opinion pilots now wrapped up and final report is being written (slight delay due to sickness absence). Report will be shared with chief officers to make decision on whether or not to roll out Care Opinion to Community Services. Administration of pilot teams now being handed back to the Feedback Team. Work continues between Strategy and Transformation and Communications and Engagement teams to embed engagement and feedback into planning and redesign protocols. Engagement Framework update report was considered by the HHSCC and CGC in November. | Ruth Fry 11/04/2024 Complete - The Care Opinion pilot has concluded and the service has been handed back to Clinical Governance/the Feedback Team. The pilot was successful with a 125% increase in stories submitted and more stories being responded to (over 51% within 7 days), more quickly and by more staff. This report has been shared with the Chief Officer for Highland HSCP along with information on the cost of extended Care Opinion to community services. The Highland 100 Panel has 30 members so far and an initial survey has been carried out. | Ruth Fry 17/06/2024 - no further update; as of the previous update all of my actions were complete. Boyd Peters 25/06/2024 - no change to report

## Board Chairs
DATE of MEETING | Board Chairs
| Exec Lead | Operational Lead | Objective | Specific Action | Status Update - Ruth Daly | Status update
Board Chairs | Director of People and Culture | Board Secretary | Training for members to enhance skills in challenge and scrutiny, particularly relating to how the board works effectively in the strategic areas. | Non Exec training plan to be developed to address training needs identified from Non Executive appraisals and succession plan. A workshop to be held to understand the current skill-sets and skills gap, particularly relating to scrutiny and challenge. Further training to be arranged to meet any skills gaps. | Discussions held with NES colleagues to deliver bespoke training for Board members using current reports and scenario workshops. Detailed programme for the session currently being prepared and the date of the session stil to be agreed | Complete - Making Data Count workshop held with Board members, with follow-up sessions to be organised by NES being discussed
Board Chairs | Executive Team | Board Secretary | Improvements to SBAR contents with clear evidence of assurance being offered to improve the Board's assurance and scrutiny role. | Report writers to record how to lift assurance to substantial within SBAR format. Further training and guidance to report authors. | Improvements to demonstrating how to lift assurance levels now being made with report writers, and updates to training materials for report writers has taken place. Additional sessions for report writers planned to take place before the end of 2023. | Complete - Board Secretary has delivered training to report writers during April and May 2024 focussing on good practice guidance, the assurance matrix and the feedback from Board and Governance Committees throughout the self evaluation exercises.
Board Chairs | Executive Team | Board Secretary | Improvements to use of assurance maturity matrix within Committee and Board meetings | Committee Chairs to use the assurance matrix to retain better oversight of business that has less than substantial assurance. Chairs to ensure Committees take an active and deliberate focus on the level of assurance during agenda preparation and during Committee meetings. | Committee Chairs have discussed the use of the assurance matrix at the Chairs' group. | Complete - further discussions held with Board Chairs on guiding committees to address the level of assurance taken at meetings.

## Staff Governance
STAFF GOVERNANCE COMMITTEE
DATE of MEETING | Exec Lead | Operational Lead | Objective | Specific Action | Previous updates | Update for July 2024 Board meeting
Staff Governance 8 November 2023 and 7 May 2024 | Director of People and Culture Chief Executive and Executive Team | Directorates & senior managers, Head of OD | Clear thread of organisational culture/ethos between front line teams and the Board. Ensure a broader systemic overview of the organisation's ethos incorporating quality, safety and practitioner outcomes with links to the performance framework. Clarity of how this is reflected in the work of governance committees with distinct reference within SBARs. | Fulfilment of the intentions of the ADP for People and Culture. | Gareth Adkins 06/09/2023 A refreshed leadership and culture framework has been discussed with the Cultural oversight group including proposals to strengthen our approach to leadership development and a learning system to support wider engagement with our staff and our leaders in practising compassionate care. This has also progressed through the area partnership forum, staff governance committee and an update provided to the board. The medical and nurse director are progressing discussions with stakeholders in relation to the externally commissioned review of our approach to quality. This will develop consensus on next steps for evolving our approach to quality. Gareth Adkins confirmed on 05/10/2023 and 11/12/2023 that there was no further updates as of yet. Gareth Adkins 11/04/2024 Culture Oversight Group continues to oversee delivery of the leadership and culture framework. Good progress against framework with refreshed leadership development programme launched on time and new staff engagement programme developed and to be progressed in 24/25. A Further area of development planned and agreed by COG are reviewing our approach to using qualitative and quantitative data to assess quality and performance across the organisation including being able to identify areas which are struggling, assess their strengths and weaknesses and offer targeted support. This will need to include a holistic approach to reviewing and using data across clinical, financial, performance and staff governance domains of quality. This would enable identification of services or teams who are struggling and then being able to assess if support is required to develop leadership and team effectiveness to support improvements in quality including team culture. In addition we have agreed to explore what more we need to do to support teams working in small communities Once we have developed and embedded these 4 elements of our leadership and culture framework we would transition to business as usual with staff governance committee receiving assurance we have a mechanism for identifying opportunities for improvement in quality and culture through effective use of qualitative and quantitative and we can support services and teams with improvement. | Gareth Adkins 26/06/2024 - Phase 1 of the Leadership and Culture programme is complete with refreshed leadership development programme in place. Phase 2 has commenced with a focus on developing our learning system and considering cohort training for key groups of managers. Staff Engagement work is progressing and will be reported on late in 2024-2025 COG has agreed to setting up short life working group to development quality assurance framework to identify teams that are struggling in one or more dimensions of quality including leadership, assessing their strengths and weaknesses and developing an appropriate action/intervention plan - this plan would be based on 5 levels of intervention including level 5 - no action required level 4 no intervention but local action plan required (no monitoring) level 3 minimal intervention with local action plan required with external monitoring level 2 - significant intervention with board level action plan and monitoring level 1 - direct management intervention with board level action plan and monitoring This will work will include consideration of teams in small communities Further work is also planned with staff governance committee, local area partnership forums, staffside and senior managers to complete development sessions on partnership working during 2024-2025
Staff Governance 8 November 2023 and 7 May 2024 | Director of People and Culture Chief Executive and Executive Team | Directorates & senior managers, Head of OD | Reframe and transition of the organisational culture/ethos with emphasis on learning and development throughout the performance framework. | Paper to Staff Governance Committee in September 2023 and initiation of the following: • Focus on developing confidence and capability of management colleagues through a review of the leadership and management programmes • Head of OD to draft a localised proposal on an established nationwide approach to assist colleagues to address staffing matters outwith formal processes and build a proposal over next 3-5 years • Training in compassionate leadership and embrace ‘Civility’ work undertaken by Helen Freeman, with colleague engagement and input • Reestablishment and refresh of Partnership working to maximise the reach of the Area Partnership Forum in terms of employee engagement • Revision of People Processes • Culture Oversight Group to be re-instated | Gareth Adkins 06/09/2023 Cultural oversight group terms of reference reviewed and group re-established and refreshed. A refreshed leadership and culture framework has been discussed with the Cultural oversight group including proposals to strengthen our approach to leadership development and a learning system to support wider engagement with our staff and our leaders in practising compassionate care. This has also progressed through the area partnership forum, staff governance committee and an update provided to the board. A programme of improvement has been established focussed on key people processes starting with recruitment. Further workstreams to be added on payroll and job evaluation Significant work already undertaken to enhance awareness and understanding of partnership working. Gareth Adkins confirmed on 05/10/2023 and 11/12/2023 that there was no further updates as of yet. Gareth Adkins 11/04/24 Culture Oversight Group continues to oversee delivery of the leadership and culture framework. Good progress against framework with refreshed leadership development programme launched on time and new staff engagement programme developed. Structured approach to improving statutory and mandatory training underway and appraisal compliance improvement plan approved by area partnership forum and Staff governance committee. Further work on partnership working planned for 24/25 including development session for APF and Staff Governance committee. | Gareth Adkins 26/06/2024 - People and Culture Portfolio board established and regular reporting to area partnership forum and staff governance committee. Work progressing well.
Staff Governance 8 November 2023 and 7 May 2024 | Director of People and Culture | Head of Comms and Engagement | Ensure engagement and communication with staff fits within the governance structure | Clarify where staff engagement sits within People and Culture. Clarify permanent ongoing resource and expectations. Establish appropriate process for reporting. Compliance with Staff Governance Standard through Staff Governance Committee and in collaboration with Area Partnership Forum on a yearly basis. | Gareth Adkins 06/09/2023 Proposal being developed on staff engagement approach building on work already undertaken to establish new methods such as listening and learning panels. Gareth Adkins confirmed on 05/10/2023 and 11/12/2023 that there was no further updates. Gareth Adkins 11/04/24 Culture Oversight Group continues to oversee delivery of the leadership and culture framework. Good progress against framework with refreshed leadership development programme launched on time and new staff engagement programme developed and to be progressed in 24/25. The staff engagement programme will link with imatter and other sources of feedback to explore staff opinions and develop organisational actions through focus groups. | Gareth Adkins 26/06/2024 - work ongoing and progressing well

## Clinical Governance & HHSCC
Clinical Governance Committee and Highland Health and Social Care Committee
DATE of MEETING | Exec Lead | Operational Lead | Objective | Specific Action | Previous updates | Update for July 2024 Board meeting
CGC 2 November 2023 and 2 May 2024 HHSC 1 November 2023 and 2 May 2024 | Director of People & Culture, Medical Director, Chief Officer Community, | Head of Comms and Engagement | Embedding patient and community representation and feedback within the performance framework and governance structure | Pilot increased publicity of Care Opinion Pilot in Community services and decision made on whether or not to expand Care Opinion to Community services Report on learnings from pilots to HHSCC and CGC in November as part of Community Engagement reporting and capture Highland HSCP assessment of the Engagement Framework's progress as part of this. Ruth D asked B Mitchell and S Chase to include on agenda for November 23 meeting on 05/10/23 Continue Highland 100 panel recruitment - ongoing to end of 2023/24 - and send out first survey by December 2023 | Ruth Fry - 15/09/2023 Pilots going well with measurable increase in stories being received and responded to. New services seeking to join the pilot. Work ongoing between Strategy and Transformation and Communications and Engagement teams to embed engagement and feedback into planning and redesign protocols. HHSCC and CGC report being drafted. Highland 100 panel contact details being collated and first survey drafted. Ruth Fry - 11/12/2023 Care Opinion pilots now wrapped up and final report is being written (slight delay due to sickness absence). Report will be shared with chief officers to make decision on whether or not to roll out Care Opinion to Community Services. Administration of pilot teams now being handed back to the Feedback Team. Work continues between Strategy and Transformation and Communications and Engagement teams to embed engagement and feedback into planning and redesign protocols. Engagement Framework update report was considered by the HHSCC and CGC in November. Ruth Fry 11/04/2024 The Care Opinion pilot has concluded and the service has been handed back to Clinical Governance/the Feedback Team. The pilot was successful with a 125% increase in stories submitted and more stories being responded to (over 51% within 7 days), more quickly and by more staff. This report has been shared with the Chief Officer for Highland HSCP along with information on the cost of extended Care Opinion to community services. The Highland 100 Panel has 30 members so far and an initial survey has been carried out. | Ruth Fry 17/06/2024 - no further update; as of the previous update all of my actions were complete. Boyd Peters 25/06/2024 - no change to report
CGC 7 March 2024 and 2 May 2024 HHSC 6 March 2023 and 8 May 2024 | Nurse Director Medical Director |  | Establish and agree a plan to implement a Quality Framework arising from recent work undertaken with Amanda Croft. | Establish a clear definition, understanding and organisational prioritisation of quality that is underpinned by patient and colleague experience, and National Guidelines. | Louise Bussell - 15/09/2023 The outcome of the Quality review has been presented and discussed at the Area Clinical Forum and is due to be presented at the Area Medical Committee (3 October) and the NMAHP Advisory Group (28 September) as part of the development of a consensus on a Quality Framework. It is going to the psychology leads meeting on 12th October and the area pharmacy committee on the 23rd October. (Just need a date for social care). Louise Bussell 12/04/2024 There is a joint development session between ACF and the Board on 23rd April focussing on the proposed quality framework to consider if it is the best fit for the work required | Boyd Peters 25/06/2024 - following the Board & ACF session, a summary note was created and the MD & ND will work with the professional leadership group (DMDs Assoc NDs AHPS etc) and also with the Exec Director Group to determine next steps. Sessions planned to occur through the summer months. The aim will be to embed quality in everything rather than to create a quality silo. Also to bear in mind the overlap between clinical governance and quality Louise Bussell and Boyd Peters 27.06.24 - The quality work to date and a proposed quality framework were presented and explored at the joint ACF and Board in April. The feedback from the session has helped shape the direction of our quality work. We have since had a session in May with clinical leaders in relation to this work and its relationship to clinical governance. We are now reviewing how we are already working across the Board prior to introducing the framework to ensure we are in a position to do this in a planned and measured way. The quality framework will be closely related to this work as patient feedback and experience is part of the rounded picture captured within the framework dataset. We have commenced a mapping exercise to understand where we are capturing patient experience effectively already, where we need to do more and where we do not have a route for feedback other than through formal processes such as complaints. This includes our position in relation to patient opinion. We are also exploring what approaches other Boards have taken.
CGC 7 March 2024 and 2 May 2024 HHSC 6 March 2024 and 8 May 2025 | Nurse Director Medical Director |  | Ensure that patient feedback is consistently collected, effectively shared, responded to and utilised across all areas of the Board. | Ensure systems and processes are developed to improve in the collection, reporting and use of patient experience feedback across the Board | Louise Bussell - 15/09/2023 Exploring approaches being utilised internally and externally in order to put forward recommendations for establishing consistent patient feedback. Louise Bussell 12/04/2025 This is going to be a longer term action as it requires considerable development work. Currently mapping out board position in order to establish a plan | Boyd Peters 25/06/2024 - no change to report

## Audit Committee
AUDIT COMMITTEE
DATE of MEETING | Exec Lead | Operational Lead | Objective | Specific Action | Previous updates | Update for July 2024 Board meeting
September Board Development Session | Medical Director |  | Board to reset its Risk Appetite | Board to refine the risk framework and refine the risk appetite statement in consultation with clinicians - to be brought back to a Board Development Session within 2023-24 | COMPLETE The Board Risk Appetite was agreed by the Board at the end of November 2023. The next phase (using the risk appetite within the strategic and operational parts of NHS Highland) will occur throughout 2024. | Boyd Peters 25.06.2024 - complete - A session for the exec directors is planned now, late July.
6 February 2024 and 21 May 2024 | Medical Director |  | Translation of revised risk appetite into workable processes for colleagues | Review and revise organisational controls in line with revised risk appetite. | Boyd Peters 28/09/2023 - Will occur during 2024 Boyd Peters 09/05/2024 - The timeline for this will run to the end of 2024, with no further update from the last Board Development session. The next step will be an exec director in group discussion, which is still awaited. No staff resource has been allocated to deliver the work, therefore, it will require action from the exec team.Expects the Exec Director Group to have further input. | Boyd Peters 25.06.2024 - No change to the comments previously given.
6 February 2024 and 21 May 2024 | Medical Director |  | Upskilling workforce in risk management knowledge and methodology | Devise and cascade organisational training to support and empower colleagues to take appropriate decisions flowing from the revised risk appetite. | Boyd Peters 28/09/2023 - Will occur during 2024 Boyd Peters 09/05/2024 - The timeline for this will run to the end of 2024, with no further update from the last Board Development session. The next step will be an exec director in group discussion, which is still awaited. No staff resource has been allocated to deliver the work, therefore, it will require action from the exec team.Expects the Exec Director Group to have further input. | Boyd Peters 25.06.2024 - No change to the comments previously given.
2023-12-01 | Director of Finance | Board Secretary | Audit Committee to include oversight of the risk process within its ToR | This is already in place. | COMPLETE

## FRP
FRP COMMITTEE
DATE of MEETING | Exec Lead | Operational Lead | Objective | Specific Action | Previous updates | Update for July 2024 Board meeting
3 November 2023 and 3 May 2024 | Deputy Chief Executive | Head of Strategy & Transformation | Performance reporting to triangulate with other NHS Highland data, including patient experience, and use trajectories, trends, and benchmarking with other Boards & systems, | Data in IPQR to include wider in-house data to assist with triangulation and to refer to any live critical issues facing NHS Highland. IPQR also to include description of trends, trajectories, and benchmark with other Boards. | Lorraine Cowie 21/12/23 - All data now has national benchmarking and a clearer description of progress made and work still to complete with timescales. All areas have trajectories where agreed and once integrated service planning is complete this will improve further. Benchmarking is available on all pages of IPR. Lorraine Cowie 16/04/24: From my perspective the IPQR ask is complete for the moment. IPQR will always evolve and how we give assurance will be an ongoing process. | Lorraine Cowie 13/06/2024 - confirmed no further update and remained complete.
2 November 2023 and 3 May 2024 | Director of Finance & Deputy Chief Executive |  | Creation of a framework for business change/service redesign to evidence the value of expenditure with links to ADP & finance. | Review proforma for approval of business cases, evolve a checklist to ensure good decisions and best value for the wider organisation. Best Value to be based on Realistic Medicine definition. | Heledd Cooper 09/10/2023 Still a work in progress and the intention is to align the financial planning, performance and workforce planning for 24/25 budget setting. Heledd is working on a document to set this out. Lorraine Cowie 21/12/23 - New Integrated Service Planning and the ADP guidance has set this out and will create a baseline for redesign. Realistic medicine has a clear project plan and is part of the strategy & transformation team. 15 box model produced by SG has a clear improvement plan developed and approved by EDG. Complete Lorraine Cowie 16/04/2024: now complete and has been reflected in process given to Board development and in the ADP/MTP. Heledd Cooper 22/04/2024: Business case proforma is being updated for review Budget setting manual was completed and Integrated service planning in place Best value documentation is being compiled. | Lorraine Cowie 13/06/2024 - confirmed no further update and remained complete. Heledd Cooper 24.06.2024: All of these actions have been completed. The business case proforma was the last item and this is complete and is being tested through the eHealth team for the EPR business case.
2 November 2023 and 3 May 2024 | Director of Finance | Board Secretary | Advisory Boards to inform and be part of the decision-making process for business change. | Hold a development session and engage with APF and ACF to initiate improvements in co-production, engagement and involvement with business change processes and governance. | Ruth Daly - Early discussions have been held with relevant individuals & joint planning session taken place. ACF and APF to hold discussions at January & February 2024 meetings on ‘Processes for business change – Advisory Board engagement’ covering staffing, Performance, Planning and Finance. | Complete APF and ACF meetings in April and May have both considered their the annual delivery plan and the Financial plan and how the respective forums can contribute to business change.
4 January 2024 and 3 May 2024 | Deputy Chief Executive | Head of Strategy & Transformation | IPQR to make explicit linkage with quality of care and outcomes. | Incorporate patient experience into IPQR with explicit reference to care and outcomes. | Lorraine Cowie 21/12/23 - LC has met with Mirian and test of change to be in March FRPC IPQR for cancer and radiology where care opinion and QPIs are embedded. Will be reviewed to expand to other areas once test of change approved. Lorraine Cowie 16/04/2024: For IPQR in terms of experience - we trialled this with cancer last time and looking at diagnostics next time on a spotlight basis. We will reflect on this approach over next 12 months and alignment with deep dives. I would say this is now complete and we will review | Lorraine Cowie 13/06/2024 - confirmed no further update and remained complete.