## Datix listing report
Level 1 - Strategic Risk Register
2022-03-01
ID | Risk - Board Objectives | Risk - Category | Next review | Description | Controls when risk identified | Risk Owner | Risk level (current) | Rating (current) | Risk level (Target) | Assurance sources | Reporting/Monitoring requirements | Responsibility ('To') | Resource requirements | Progress | Due date | Done date
632 | A Great Place to Work | Workforce | 2021-11-30 | There is a risk that attempts to improve the culture of the organisation are not sustained or successful. This could impact on recruitment, retention, colleague experience, reputation and performance as well as patient confidence in the organisation. Changing the culture will take a significant period of time and during this there remains a potential for staff not to feel valued, respected and listened to, despite ongoing efforts | The Culture Programme has been ongoing since July 2019 and continues to regularly report on progress with its to the Board and Staff Governance Committee . Putting in place good speak up mechanisms and support as well as delivering on longer term transformation elements | Hogg, Fiona | High | 120 | Medium | NHSH Staff Governance Committee | Culture Fit for the Future action plan has been developed. | Hogg, Fiona | Culture Fit for the Future Steering Group Board SLT & Non-Execs Staff Governance | Action Plan in place | 2019-10-30 | 2019-10-30
[11 empty] | Development of KPis and risks order to monitor the Culture Programme Plan | Hogg, Fiona | Culture Tools and Metrics Workstream Culture Oversight Group Staff Governance Committee | Implementing a culture programme dashboard reporting system to feed into Staff Governance, EDG and NHSH Board. 1st report due by end of May 2021. KPIs developed and agreed | 2021-05-31 | 2021-05-31
[11 empty] | Culture Oversight Group and Programme structure established and overseeing progress with good engagement across the organisation | Hogg, Fiona | Culture Advisor, Director of HR, Workstream leads, Staffside, SMEs | Meetings of the COG have been held monthly of this group and it’s predecessor since Nov 2019. Minutes are reviewed at Staff Governance committee. There is also a rhythm of workstream and workstream lead meetings. The future structure will be reviewed over the coming months. | 2022-06-30
[11 empty] | Culture Programme of Work for 2021/22 to be developed. | Hogg, Fiona |  | " Ongoing as part of the Culture Metrics and Tools Workstream - IPQR has already had additional metrics included since July 2021, delayed recruitment for additional capacity in analytics means that work will be completed now by 31 March 2022 " | 2021-05-31 | 2021-05-31
[11 empty] | Purchase and implementation of a system to monitor culture within the Board. | Hogg, Fiona |  | Culture app being launched, first report due in June 2021. Complete ongoing reporting | 2021-06-30 | 2021-06-30
[11 empty] | Operational Culture Forums to be developed. | Hogg, Fiona |  | Argyll & Bute group in operation since summer 2020. Acute group has now been set up since August 2021. Community and Corporate services approaches to be considered with new people partners. This date has been moved to 31 May 2022 due to systems pressures | 2022-05-31
[11 empty] | Further development of the culture programme of work and additional KPIs to be developed | Hogg, Fiona |  | "The culture programme plan is being updated and a wellbeing workstream added and Civility plan prepared, and IRP actions included in the tracking, to form the work plan for the year ahead to allow for integrated planning . This has been delatyed e to step down of some meetings due to systems pressures. Wellbeing was added to report in January 2022. " """ | 2022-05-31
[11 empty] | Further work is needed to address our risk and safety culture across the organisation, including improvements to our compliance with statutory and mandatory training compliance | Hogg, Fiona | " | An audit and root cause analysis of our challenges with statutory and mandatory training is underway and will report to May audit committee, where a detailed plan to address will be set out | 2022-05-31
662 | Clinically & Care Excellence | Clinical Strategy and Redesign | 2021-11-30 | There is a risk that in the absence of a NHSH Clinical and Care Strategy being in place, that the organisational efforts lack coherence and as such some aspects of business are not fully aligned to a collective organisational goal. | National policy and direction in coherence through a variety of strategic document. Daily correspondence relating to new risks and considerations are received and processed through EDG and SLT. NHSH Remobilisation Plan has been established in line with national policy and strategy. NHS Remobilisation plan is being assessed by Scottish Government departments to ensure commitments are coherent with national requirements. NHSH Remobilisation Plan was developed with inclusion of all department leadership team, Highland Partnership Forum and the Area Clinical Forum and aligned Professional Advisory Groups. The DCO has an objective to complete the strategy for NHSH by Dec 2020. DPH is reviewing the strategic needs assessment post COVIDE peak to ensure needs and service configuration are a match. Project Management Office and approach in place to drive forward redesign, improvement and recovery. | Park, David | Medium | 90 | Medium | NHSH Clinical Governance Committee | Robust programme management approach has been identified and programme manager recruited and in post. |  | Director of Strategic Commissioning, Planning & Performance Clinical Strategy Programme Manager | Programme Manager in post. |  | 2019-10-30
[11 empty] | Programme plan to be developed. |  | Director of Strategic Commissioning, Planning and Performance. Clinical Strategy Programme Manager | Plan developed - will be monitored by the Strategy Steering Group which has been formed and will meet from 23 January 2020. | 2019-11-30 | 2019-11-30
[11 empty] | Strategy Steering Group has been formed and will commence meeting in January 2020. |  | Director of Strategic Commissioning, Planning and Performance Programme Manager | Strategy Group commencing meeting on 23 January 2020. | 2020-01-23 | 2020-01-10
[11 empty] | Governance structure and format to be developed in order to report on progress of the programme with the Board and Steering Group. | Park, David | Head of Strategy and Transformation | Paper being presented to board with defined structure on 28/9 | 2021-11-30
[11 empty] | Development of 1 year Strategy and Remobilisation Plan | Park, David | CEO, Deputy CEO | Board Development session to be held May 2021. Plan agreed and in place |  | 2021-07-15
[11 empty] | Recruitment of Head of Strategy and Transformation to lead this work. | Park, David | Deputy CEO | May 2021 Recruitment under way. Appointment has been made and awaiting individual to take up post. |  | 2021-07-15
[11 empty] | NHS Highland Clinical and Care Strategy 3 - 5 year plan to be developed to establish long term plan. | Park, David | Deputy CEO | Updates presented regularly to Board/Board Development. Due to Omicron new timelines will need to be agreed. | 2022-03-31
[11 empty] | Remobilisation Plan will to be submitted to SG by September 2021 | Park, David |  | Publication of RMP4 being presented to board in January 2021 which will finalise. | 2021-09-30 | 2021-09-30
666 | Safe & Sustainable | IT and Digital | 2021-10-29 | There is a risk that NHS Highlands ability to deliver normal service could be severely disrupted by a major cyber incident. This is because NHS Highland's increasing reliance on digital solutions to deliver its services. This will result in increased likelihood of NHS Highland suffering clinical, financial and reputational damage in the event of a significant cyber incident occurring. | A layered security model has been implemented Endpoint devices and servers have operating system patches applied in a scheduled manner. Endpoint devices and servers have anti virus software installed and configured to automatically update. Secondary care laptops and desktops have been upgraded to Microsoft Windows 10 operating system. Microsoft Advanced Threat Protection (ATP) has been installed on Windows 10 endpoint devices. NHS Firewall infrastructure has been upgraded to improve perimeter security. NHS Highland has taken steps to ensure that our infrastructure meets the minimum baseline security standards required for Caber Essentials certification. NHS Highland have implemented the Trend Deep Security Tool. This tool mitigates disclosed vulnerabilities in out of support operating systems. Outpost 24 Hacker in a Box vulnerability scanner is used to perform scans against the secondary care server estate. NHS Highland operates a mufti-site server infrastructure to provide digital resilience NHS Highland has implemented a robust commvault backup system. | Park, David | High | 160 | High | NHSH Finance, Resources and Performance Committee | NHSH updated firewall infrastructure to improve perimeter security. |  | NHSH eHealth Network Team | Firewall activity logs evidence the level of malicious traffic blocked. |  | 2019-10-30
[11 empty] | NHSH has taken steps to ensure that IT infrastructure meets the minimum baseline security standards required for Cyber Essentials Certification. | Ross, Iain | NHSH have been independently assessed by NSS who are the accredited assessors. | NHSH have achieved Cyber Essentials Certification. March 2022 NHSH CE certificate has since expired and a recertification exercise will be required | 2022-12-31
[11 empty] | Work is ongoing to achieve Cyber Essentials Plus certification, however this is dependent on the delivery of national projects such as the MS Office 365. | Ross, Iain | eHealth Delivery Group Director of Strategic Commissioning, Planning & Performance (SIRO) | A cyber resilience group is being set up with one of the remits to start the re-certification process to achieve cyber essentials plus certification March 2022 The CE+ certification criteria is being updated by the provider. Once published the roadmap to compliance will be considered by the Digital Resilience Group. | 2022-12-30
[11 empty] | NHSH are in the process of updating the operating systems used on servers and endpoint devices to modern supported versions. | Ross, Iain | National Cyber Security Centre. | Windows 10 rollout progressing, Secondary Care is finalising. Primary Care is provisionally expected to complete April 2022. Extended support from Microsoft purchased via a national contract. | 2022-12-31
[11 empty] | NHS Scotland has developed a compliance tracking tool that documents the security controls to which NHS Highland must evidence compliance. This tool covers the controls for the key frameworks that form the NHS cyber secrutiy landscape: NIS, Information Security Policy Framework, Public Sector Action Plan on Cyber, ISO27001. The eHealth department have initiated a cyber security project to conduct a gap analysis against the 200+ controls in order to have visibility of the Board's overall cyber framework compliance status | Ross, Iain | Information Assurance & Security Manager Director of Strategic Commissioning, Planning and Performance (SIRO) | COVID 19 disrupted this piece of work. A documentation audit is being conducted 26th June by the NIS Competent Authority. The cyber security project will recommence after the documentation audit completes. New framework issued March 2022 this piece of work will now fall under the digital resilience group. Gap analysis to be conducted against all NHS Highland digital estate. | 2022-09-30
[11 empty] | Develop an action plan based on the results of the cyber framework gap analysis and initiate a program of work to implement resolutiona and mitigations. | Ross, Iain | Cyber Security Project Information Assurance & IT Security Manager Director of Strategic Commissioning, Planning & Performance (SIRO) | COVID 19 disrupted this piece of work. A documentation audit is being conducted by 26th June by the NIS Competent Authority. The audit report is expected to define the action plan. The audit will also provide the timescales required to achieve compliance against the control list. Complete March 2022 This piece of work will now fall under the digital resilience group. Gap analysis to be conducted against all NHSH digital estate. Full compliance to the NIS controls is a long term project. | 2022-08-31
[11 empty] | NSS are in the early stages of developing a national Security Operations Centre to provide a centralised operational security function. SOC functionality increasing. ATP monitored at a national level. Dedicated threat hunting staff being employed. SPLUNK SIEM solution being evaluated as a national offering. | Ross, Iain | NSS (will define timescale) Information Assurance & IT Security Manager Director of Strategic Commissioning, Planning & Performance | "new centre now in place. Mar22 - the Cyber Centre of Excellence is operational and acting as the coordination point for national cyber security. The service offerings will expand as national toolsets are implemented ." | 2020-09-30 | 2021-07-16
[11 empty] | NHS Highland have rolled Microsoft ATP to all secondary care endpoints. |  | NHS Highland IA & IT Security Team. NSS National SOC | "NHS Highland have investigated a small number of events identified in the ATP dashboard. NSS SOC have flagged the same events. Mar 22 - This action is complete and ATP monitoring is now a BAU activity" Mar 22 - This action is complete and ATP monitoring is now a BAU activity" |  | 2020-06-17
[11 empty] | NHS Highland are in the process of rolling out Trend Deep Security Tool. This tool mitigates disclosed vulnerabilities in out of support operating systems. |  | NHS Highland eHealth | "Vendor documenation and commercial reviews. Mar 22 - Trend Deep Security is operational for North Highland, Network configuration required to extend coverage to A&B and Primary care. " | 2022-06-30
[11 empty] | Setting up a cyber resilience group | Ross, Iain |  | "The new group will oversee key pieces of work including re-certification of cyber essential plus. The intitial meeting of the Cyber Resilience Group is set for 13th October 2021." | 2021-10-29
[11 empty] | Purchase and implementation of the Varonis system to manage data | Ross, Iain |  | Varonis has been purchased and is being implemented. Varonis implemented and currently analysing he network to normalise data and user activity. March 2022 this action is complete and Varonis alert remediation is BAU activity | 2021-10-29 | 2022-03-01
[11 empty] | Scottish Public Sector Cyber Resilience Framework has published new measures which require audit against compliance | Ross, Iain | e Health Cyber Resilience Group | "Audit will required to be undertaken on annual basis, Baseline audit to be undertaken. NIS audit for 2021 has been conducted, CRG will take forward NIS compliance program to improve cyber resilience. NIS self assessment to be submitted 2023, next full NIS audit is scheduled for 2024. " | 2024-05-30
[11 empty] | National Cyber of Excellence now established. 5 year plan to be fully developed. | Ross, Iain |  | Currently into year 3 | 2023-12-29
[11 empty] | Microsoft 365 security tools being implemented as part of MS 365 project | Ross, Iain |  | "MS Defender for endpoint rolled out to NHSH desktop and laptop devices. National workshops being conducted to develop the security design documentation." March 2022 MS365 security features are currently being implemented. | 2022-06-30
[11 empty] | Digital Resilience Group response to the heightened state sponsored cyber security risk | Ross, Iain |  | "Mar 22 - An operational group has been set up to take actions to reduce NHS Highlands attack surface and minimise the risks presented from state sponsored cyber activity. NCSC, Scottish Government and NSS have produced recommended actions, these will be considered implemented and tracked by the DRG" | 2022-03-15
706 | A Great Place to Work | Workforce | 2021-11-30 | There is a risk to service delivery due to the increasing age profile of the workforce combined with challenges to recruit and retain all of the required workforce due to national and local capacity, capability and infrastructure | Our 2022/25 workforce plan is being developed alongside our organisational strategy and workforce planning capacity has been increased. Local teams have been participating in workforce reviews to understand and mitigate their key risks. | Hogg, Fiona | High | 120 | Medium | NHSH Staff Governance Committee | Launch a Workforce Board for oversight and setting up of workstreams to look specifically at recruitment and attraction, succession planning and retention. in order to develop a clearly defined strategy. | Hogg, Fiona | Workforce Board. | "Board in place since early 2021. Workshops held in June / July and findings presented, priority areas anc actions agreed, workstreams now being set up to take forward a plan to address the key issues found. This action is now closed and workstreams will provide their own specific actions by 31/12/2021 " | 2021-01-01
[11 empty] | Employee Assistance Programme in place to support staff at work, aiding retention. | Hogg, Fiona |  | Ongoing provision with Validium Group, commenced in May 2020. |  | 2020-05-01
[11 empty] | Independent Guardian Service to be set up for employees to discuss their concerns relating to patient care and safety, whistle blowing, bullying and harassment and work grievances. | Hogg, Fiona |  | In place since August 2020, provided by Derek McIlroy and Julie McAndrew. "Meet the Guardians" sessions set up and communications throughout NHSH to raise awareness. |  | 2021-02-28
[11 empty] | Identify proactive solutions to mitigate recruitment shortages and to translate into effective 3 year workforce plans from 1 April 2022 | Hogg, Fiona |  | " Working with the NTC team to collabroate on promotion, marketing and attendace at Job Fairs, working group in place, International recruitment being progressed with North boards, additional recruitment resource being funded and clinical and leadership engagement and detailed demand planning underway " | 2022-08-31
[11 empty] | New approach to volume recruitment "always on" proactive and centralised process to ensure consistent level of workforce is available | Hogg, Fiona |  | "Initial advert for nursing roles and central selection process has been rolled out and is being reviewed and fine tuned. On track to be fine tuned and wider roll out planned for 2022 " | 2021-12-31 | 2021-12-31
[11 empty] | New approach to volume recruitment "always on" proactive and centralised process to ensure consistent level of workforce is available | Hogg, Fiona |  | Review of Phases 1-3 nurse recruitment now underway and planning for year ahead taking place to be agreed by end April 2022 | 2022-04-30
[11 empty] | Workforce board to define and agree the additonal actions needed to mitigate this risk and reflect all the work underway | Hogg, Fiona |  | Workstreams now in place with key objectives and are defining their detailed plans and the associated risks to update this register. | 2022-05-31
[11 empty] | Workforce board to define and agree the additonal actions needed to mitigate this risk and reflect all the work underway | Hogg, Fiona |  | Agenda item for 4 October workforce board | 2021-10-31 | 2021-10-31
712 | Safe & Sustainable | Estates and Facilities | 2022-02-28 | There is a risk to patient safety and operational capacity from fire due to Raigmore Hospital's fire compartmentation not meeting current building standards. | The programme of work needs to be paced at the level of disruption the hospital can stand. This will need to be factored into the forward operational plans so a decant ward can be maintained to allow this work to proceed. Funding is also needed for the remainder of the work. This involves refurbishment in each ward, installing sprinklers and upgrading compartments. This programme has completed about 50% of the sleeping accommodation and will deal with maternity this year but further work is needed in the tower block. | Wilson, Alan | High | 160 | Medium | NHSH Board, NHSH Estates, Facilities & Decontamination Team Meeting, NHSH Finance, Resources and Performance Committee, NHSH Health & Safety Committee | Approached SG for additional £1m funding to carry out additional work. | Wilson, Alan |  | Update on 22 Sept funding agreed at £500k due to time constraints to complete work
[11 empty] | Require access to Raigmore Hospital to complete the work | Wilson, Alan |  | agreed programme with service managers. New programme has been developed due to current systems pressures and following Scottish Fire Service visit and request to update |  | 2021-12-20
[11 empty] | Plans to be developed to complete the work | Wilson, Alan |  | Longer term strategy for completion of all works being processed and agreed | 2022-03-01
714 | Safe & Sustainable | Estates and Facilities | 2022-05-18 | There is a risk that the amount of funding available to invest in current backlog maintence will not reduce the overall backlog figure. | The current funding budgets both capital and revenue are not able to reduce the current backlog maintence figures. We currently apply a risk based methodology to priortise investment. | Wilson, Alan | High | 120 | Medium | NHSH Asset Management Group, NHSH Finance, Resources and Performance Committee, NHSH Health & Safety Committee, Operational Unit - Health & Safety Committee | Programme of building surveillance every 5 years to identify and prioritise programme of work. | Wilson, Alan | Head of Estates, Facilities and Decontamination | Ongoing with annual plan being submitted to the SG
[11 empty] | Capital investment programme utilising risk analysis allowing prioritisation of works representing the greatest risk to NHSH | Wilson, Alan | Director of Estates, Facilities and Decontamination | Ongoing
[11 empty] | Replacement building programmes instigated. | Wilson, Alan | Director of Estates, Facilities and Decontamination | Ongoing hospital developments in Skye and Aviemore. Planning ongoing regarding redesign for Belford and North Coast
715 | Safe & Sustainable | Public Health | 2022-02-28 | There is a risk that there will be poor health outcomes from resurgence of COVID-19 and the effects of seasonal influenza. There is also a risk of significant disruption to services resulting from both disease occurence and the impact of control measures. | Considerable work has been undertaken to control COVID-19 through lock down, infection control and testing. The remobilisation plan id designed to balance and return to more normal health services with continued protection against COVID-19. An expanded immunisation programme is planned to mitigate influenza risk and measure will be put in place for COVID immunisation when an effective vaccine is available. Winter planning includes measures to addess these risks. | Allison, Dr Tim | Very High | 200 | High | NHSH Clinical Governance Committee | Co-ordination and delivery of influenza immunisation programme. | Allison, Dr Tim | Public Health | Improved uptake rates for most recent programme.complete | 2021-06-30 | 2021-07-16
[11 empty] | Co-ordination and delivery of COVID case management, testing and immunisation programmes | Allison, Dr Tim | Public Health | Successful test and trace, widespread test availability and good immunisation rates achieved. Complete | 2022-03-31 | 2021-07-16
[11 empty] | Social mitigation strategy and action plan drawn up. | Allison, Dr Tim | Public Health | Paper presented to the Board on 25 May 2021 Workshop taking place 03/11/21 | 2022-03-31 | 2021-07-16
[11 empty] | Addressing the impact of COVID 19 on services is covered under risk 123. | Park, David |  | See actions for ID123
[11 empty] | Implementation of the action plan. | Allison, Dr Tim |  | Progress with implementation. Plans for covid have been on schedule | 2021-09-30 | 2021-09-30
[11 empty] | Co-ordination and delivery of COVID case management, testing and contact tracing | Allison, Dr Tim |  | Activities continue to be in line with government policy and in light of local circumstances and guidance | 2022-03-31
[11 empty] | co-ordination and deliver of tranche 2 of flu and covid immunisation | Allison, Dr Tim | Vaccination oversight group | See risk 959 | 2022-03-31
[11 empty] | Implementation of the Social Mitigation Strategy action plan | Allison, Dr Tim | Substantive arrangements need to be set up but reporting goes through to EDG | Implementation workshops have commenced
830 | Safe & Sustainable | Finance / Sustainability (ensuring value and sustainability) | 2021-11-30 | There is a risk of unplanned expenditure and non delivery of savings due to ongoing financial uncertainties, as a result of the pandemic, resulting in failure to deliver against financial targets for 2021/22 and compromising the return to financial balance. | NHS Highland has an underlying deficit of 39.5 million. The Board is not expecting to meet its financial targets until year 3, 2021/22. Significant uncertainty around COVID expenditure and funding along with the implications of remobilisation and the level of pressure within the health system have increased the level of risk in the current financial year. Implementation of the remobilisation plan along with engagement and ownership from clinical and care professionals is crucial. FRB remobilised with focus on appropriate workstreams. PRB established. Reinvigoration of grip and control measures to reinforce messages. Reengagement with THC and formation of a programme board. Close engagement with Scottish Government. | Garden, David | Medium | 90 | High | NHSH Finance, Resources and Performance Committee | Project Management Office looking at efficiency and productivity savings through a number of workstreams. |  | Finance, Resources and Performance Committee | ongoing PMO Reports to the Financial Recovery Board and Finance Committee |  | 2021-04-01
[11 empty] | Continual monitoring of monthly performance over the final part of the year with appropriate actions taken to mitigate any deviation from plan to ensure that the financial targets are met. |  | Director of Finance | Monthly reporting during 2021/22 to Director of Finance. | 2020-03-31 | 2021-04-01
[11 empty] | Development of a NHS Highland clinical and care strategy with a clearly defined timeline for implementation (links to risk 662 re: clinical care strategy). | Park, David | Director of Strategic Commissioning, Planning & Performance |  | 2022-12-31
[11 empty] | Performance Recovery Programme Board has been set up and will operate in a similar way to FRB re mobilisation and performance. |  | Finance, Resources and Performance Committee. | Will report to Finance, Resources and Performance Committee. |  | 2020-06-24
[11 empty] | Controls put in palce around COVID expenditure to ensure that appropriate approval are obtained and included in the plan. |  | Director of Finance | COVID mobilisation plan submitted to Government. |  | 2020-06-18
[11 empty] | Regular communication with Scottish Government re: COVID funding. | Garden, David | Director of Finance | Weekly reporting initially during 2020/21. Ongoing reporting to the SG | 2021-12-31
[11 empty] | Controls for remobilisation to be put in place. | Garden, David | Director of Finance | ongoing work to ensure financial plans in place | 2021-12-31
[11 empty] | Establishment of a future joint PMO with the Highland Council to scrutinize adult social care cost improvement schemes. | Garden, David |  | Ongoing. work complete |  | 2021-07-15
877 | Partners in Care | Clinical Strategy and Redesign | 2021-11-30 | There is a risk of services being designed and delivered in ways that make them unsuitable or inaccessible to some people; because of lack of resourcing of, or commitment to, partnership working and engagement, leading to poorer health outcomes and reduced wellbeing for people in Highland and Argyll & Bute, and damaging the performance and reputation of NHS Highland. | Argyll & Bute HSCP engagement framework is already in place. This sets out good practice for engagement. Good progress is being made with the NHSH engagement framework and Communications and Engagement Strategy has been approved. | Hogg, Fiona | High | 160 | Medium | NHSH Staff Governance Committee | NHSH Communications and Engagement Strategy and Annual Action Plan to be developed to assign resources to organisational priorities for communications and engagement. Team and individual development plans will be aligned. | Hogg, Fiona | Ruth Fry Staff Governance Committee | Strategy regularly reported on to the Staff Governance Committee and progress is monitored via internal and external feedback channels. Strategy and action plan has been developed and approved. | 2021-06-30 | 2021-07-21
[11 empty] | Training for communications and engagement. | Hogg, Fiona | Ruth Fry Staff Governance. | Bitesize training sessions with good feedback received and more sessions planned. Full long term training plan being put in place. Complete | 2021-10-31 | 2021-12-31
[11 empty] | NHSH Engagement Framework to be developed to set out good practice, with signposting, examples, training and toolkits, and provide assurance via an oversight group. Completed engagement plans will provide evidence. | Hogg, Fiona | Ruth Fry Staff Governance | Framework Already in place for Argyll & Bute. A SLWG has been established for Highland. A Permanent community engagement manager and engagement co-ordinator have been appointed. | 2021-06-30 | 2021-07-21
[11 empty] | Next phase of actions to mitigate this risk to be agreed and included | Hogg, Fiona |  | Launch of together we care engagement approach. | 2021-11-30 | 2021-11-30
[11 empty] | Strategy development approach is now being rolled out. Further actions will be agreed | Hogg, Fiona |  | Launch of together we care engagement approach. | 2021-11-30 | 2021-11-30
959 | Clinically & Care Excellence | Public Health | 2022-02-28 | There is a risk that the vaccination programmes for influenza and COVID will not be effectively and efficiently delivered leading to reduced population immunity and reputational damage. | Arrangements for the oversight and delivery of influenza and COVID vaccination have been in place since November 2020 for COVID vaccination and for much longer for influenza. Staff have been deployed for vaccination and primary care arrangements are longstanding. The vaccination oversight group reports to the Executive Directors Group. | Allison, Dr Tim | High | 160 | Medium | NHSH Board, NHSH Clinical Governance Committee | Delivery of influenza vaccination to appropriate cohorts by December 2021 | Allison, Dr Tim |  | Uptake has exceeded that for 2020/21 and is close to 80% of those eligible. The programme has been paused nationally to focus on COVID | 2021-12-31 | 2021-12-31
[11 empty] | Delivery of COVID vaccination in line with tranche 2 requirements by December 2021 | Allison, Dr Tim | Uptake has exceeded the target of 80% of those eligible getting a booster by the end of 2021 | Uptake has exceeded the target of 80% of the eligible a booster by the end of 2021 | 2021-12-31 | 2021-12-31
[11 empty] | Implementation of the Vaccine Transformation programme by 31 March 2022 | Allison, Dr Tim | Modelling work has been undertaken including for finance and staffing |  | 2022-03-31
123 | Safe & Sustainable | Finance and Performance | 2022-02-28 | There is a risk that the performance of the health and care system is compromised in remobilisation due to the number of constraints posed by COVID 19, winter pressures and those pressure inherent in the system pre-COVID 19, NHSH is unable to meet national targets. | A Performance Recovery Board established that meets weekly. Drive forward improvement in performance whilst maintaining oversight of the implications of COVID 10 should further waves of activity occur. Support the recovery and maintenance of the scheduled and unscheduled care pathways through surveillance of delays and redesign of patient pathways whilst also looking to incorporate winder planning arrangements. Ensure whole system readiness to deliver high quality patient pathways and excepted levels of performance. Data driven processes in place to ensure close surveillance of the system and 10 workstreams identified within a programme of work to address areas of under performance linking to redesign. Surveillance of the performance of the mobilisation plan. | Park, David | Very High | 200 | Medium | NHSH Finance, Resources and Performance Committee | PMO Workstream for outpatients. | Park, David | Director of Acute Services | Ongoing monitoring through PMO Office, Workstream Project Board and Financial Recovery Board. Complete | 2020-03-31 | 2021-07-15
[11 empty] | Scottish Government scrutiny. Helping to share good practice from other health boards around Scotland. |  | Scottish Government | Following SG Visit confirmation received that the information provided by Planning and Performance to the operational Units is very good. |  | 2019-10-30
[11 empty] | PMO Workstream for theatres | Park, David | Director of Strategic Commissioning, Planning & Performance | Ongoing monitoring through PMO Office, Workstream Project Board and Financial Recovery Board. Work complete | 2020-03-31 | 2021-07-15
[11 empty] | Revised Performance Governance Structure agreed with an associated reporting framework. |  | Planning and Performance Operational Units | Reporting system approved by SLT - 30/09/2019. Reports to Service Managers Reports to the Board. |  | 2019-09-30
[11 empty] | NHSH Remobilisation Plan. |  | Deputy CEO | Development of specialty level remobilisation plan with funding agreed / approved. |  | 2021-05-19
[11 empty] | Monitoring of performance against remobilisation plan. | Park, David | Head of Strategy and Transformation | Appropriate governance through individual programme boards and through Performance Recovery Board covering all aspects of RMP4 that are appropriate. | 2021-12-30 | 2022-01-13
[11 empty] | Bed modelling and patient flow workstreams / projects ongoing. | Park, David | Head of Strategy and Transformation | This will be completed through Home is Best Programme Board as we need to develop a whole system approach. | 2021-12-31 | 2022-01-13
[11 empty] | Review of unscheduled care being managed through performance review and dedicated Project. | Park, David |  | Managed through performance review and dedicated Project. complete |  | 2021-07-15
[11 empty] | Establishment of a SLWG for nurse recruitment | Hogg, Fiona |  | SLWG has been set up under leadership of the deputy HR Director | 2021-08-31 | 2021-09-23