## Slide 1: NHS Highland Culture Programme Programme report to NHS Highland Board 29 March 2022
RAG definitions
Amber
Green
Red
Programme, project or milestone is at significant risk of failure to deliver projected benefits and / or major slippage in time / resource
Programme, project or milestone is at risk of failing to deliver the projected benefits and / or is behind delivery schedule
Programme, project or milestone is on track for delivery (on time, to budget, forecast benefits)

## Slide 2
Overall Culture
Programme Status
Achieved in last quarter (Jan – Mar 22)
Progressed Culture planning for 22/23 with People Leadership team and assessed resource requirements and priorities Analysed the results of the Listening and Learning partnership survey following survey closure in Mid January Progressed development of Wellbeing strategic themes and priorities and conducted initial testing with stakeholder group Leaflet highlighting options for staff support developed and circulated
Programme Status
Report Date: 9th March 2022
Green
Planned for next quarter (March 22 – June 22)
Finalise Culture Programme planning for 2022/23 Complete first pass development of a culture metrics ‘dashboard’ (will require further development post 1st iteration) Roll-out Exit and On-boarding Surveys as part of the Culture Amp platform Progress the scoping of the ‘Promoting Professionalism’ (Civility Saves Lives) possible implementation options Re-start Team Conversations pilots and the Leadership and Management Development programmes
Risks / Issues | Mitigating Actions | Owner | Progress
(RISK) There is a risk that the capacity of the People and Culture team to address the 2022/23 Culture priorities in light of the wider strategic priorities will be constrained | Solid planning and prioritisation for the function; with clear set of choices for EDG / Board in terms of the activities and resource implications. Ongoing restructure of the function. | FH / GB | Planning progressing well – requires full resourcing assessment in order to allow senior input and prioritisation decisions
(RISK) There is a risk that due to organisational pressures (COVID, Winter) staff capacity to engage in culture development activities is severely reduced | Team Conversations was paused for roll-out during current Covid peak. Activities requiring less colleague engagement prioritised as well as ongoing focus on wellbeing. | EDG / SysLT | Team Conversations and Leadership and Management Development activities to restart in March reflecting reduced systems pressure.

## Slide 3
Values & Behaviours
Achieved in last quarter (Jan – March 22)
Team Conversations were paused during this quarter due to Systems pressures. The pilots are likely to be able to proceed during March.
Priority Status
Report Date: 9th March 2022
Green
Planned for next quarter (March 22- June 22)
Hold pilots for Team Conversations and evaluate Determine resourcing model / support for Team Conversations Finalise design of reward and recognition scheme and test and communicate across the organisation
Milestone | Date | RAG
Launch Values Animation to all staff | 1st December 2021 | Completed
Hold and evaluate Culture “Team Conversation” pilots | Updated to start in March 2022 | Team Conversations will now start roll out in March
Reminder of Scope
Definition and roll-out of a new vision and set of strategic objectives for NHS Highland Communication and embedding of the NHS Scotland values across the organisation, with shared understanding of what these means in terms of expected behaviours and ways of working Definition and roll-out of a visual (brand i.e. to replace the HQA) and tools to support the dissemination of the vision, values and objectives
Risks | Mitigating Actions | Owner | Progress
There is a risk that due to organisational pressures (COVID, Winter) staff capacity to engage in culture development activities is severely reduced | Team Conversations has been paused for roll-out during current Covid peak. Activities requiring less colleague engagement prioritised as well as ongoing focus on wellbeing. | EDG | Team Conversations and Leadership and Management Development activities to restart in March reflecting reduced systems pressure

## Slide 4
Civility Saves Lives
Priority Status
Report Date: 9th March 2022
Amber
Reminder of Scope
Communication and embedding of the core tenets of CSL throughout NHSH, working closely with values and behaviours to ensure integrated messaging Design and roll-out of materials and tools to support teams explore the “calling it out with compassion” approach Assessment of efficacy of CSL via quantitative/ qualitative survey
Achieved in last quarter (Jan 22 – March 22)
Discussions on approach to Promoting Professionalism progressing, with roll-out options under development Meeting in diary for 4 March to progress planning and agree option
Planned for next quarter (March – June 22)
Progress discussion on approach to promoting professionalism (Vanderbilt) Communicate / share approach to Civility Saves Lives and Promoting Professionalism across the organisation
Risks | Mitigating Actions | Owner | Progress
There is a risk that due to organisational pressures (COVID, Winter) staff capacity to engage in culture development activities is severely reduced | Team Conversations has been paused for roll-out during current Covid peak. Activities requiring less colleague engagement prioritised as well as ongoing focus on wellbeing. | EDG | Team Conversations and Leadership and Management Development activities to restart in March reflecting reduced systems pressure
Milestone | Date | RAG
Hold and evaluate Culture “Team Conversation” pilots | Moved to March 2022 | Team Conversations will now start March 2022
Launch Poster Campaign (Civility) | TBC | Posters completed, awaiting rollout plan
Agree plan for Promoting Professionalism | March 2022 | Meeting on 4 March 2022 to progress

## Slide 5
Leadership & Management
Development
Achieved in last quarter (Jan - March 22)
Leadership and Management Development learning sessions paused due to Systems pressures impacting ability to attend Replanning is now underway, rescheduled dates have been agreed from March nd a refresher session is also in development
Priority Status
Report Date: 9th March 2022
Green
Planned for next quarter (March – June 22)
Complete development of Phase 2 Leadership and Management Development modules Launch Courageous Conversations e-learning module Re-start cohorts for Leadership and Management Development
Reminder of Scope
Developing and implementing a leadership and management framework Design and deliver an open and transparent process for embarking upon a programme of development Design and deliver a suite of learning materials that will deliver the programme Explore and deliver other mechanisms of support (beyond learning), for example peer support, action learning sets and coaching Design and delivery of a clear learning pathway to support Managers to have career conversations with their teams development available for all Design and delivery of a promotion and evaluation approach to all aspects of the leadership and management development programme
Milestone | Date | RAG
All Phase 1 Leadership module development complete | 30th September | Completed
Hold and evaluate Culture “Team Conversation” pilots | Reforecast to March 2022 | Team Conversations will now start roll out in March
Risk as for Values and Behaviours and Civility

## Slide 6
Culture Metrics and Tools
Priority Status
Report Date: 9th March 2022
Amber
Reminder of Scope
Define and agree a set of metrics to be included within the Integrated Performance Report (under Staff Governance) Design and delivery of regular culture dashboard, allowing identification of areas / departments that may require support Delivery of a one-off (or regular) tool for conducting culture assessment / survey (complementary to rather than duplicating iMatter)
Achieved in last quarter (Jan - March 22)
Ongoing analysis and sharing of results at team / departmental level Listening and Learning events held Listening and Learning Partner Survey (for non-employees) closed and results analysed
Planned for next quarter (March – June 22)
Progress development of “Culture dashboard” bringing together other key metrics (e.g. absence rates) Continue to hold staff focus groups and ‘Listening and Learning’ events to understand feedback and themes Implement exit and on-boarding surveys as part of the Culture Amp platform
Risks | Mitigating Actions | Owner | Progress
There is a risk that staff do not perceive / feel action is being taken to respond to survey feedback (which was a key finding of the survey results) | Clear focus on one priority action in response to survey feedback; combined with series of focus groups and leadership roadshows to engage and listen to staff | EDG | Senior leadership visibility and clarity of strategic objectives prioritised with a number of strategy sessions held and EDG visits across the Region.
Milestone | Date | RAG
Survey results and communications fully cascaded | From 30th June 2021 | Complete
Roll out non employed culture survey | 31 Dec 2021 | Complete
Development of culture dashboard | Revised to 30 June 2022 | Workforce Analyst now onboarded so this work can commence

## Slide 7
People Processes
Achieved in last quarter (Jan – March 22)
Tool to support people process timeline planning / management developed and in use to be tested Reporting of people process case metrics continues
Priority Status
Report Date: 9th March 2022
Green
Planned for next quarter (March - June 22)
Progress procurement of case management system Ongoing improvement to people process reporting / timelines Further development of people process feedback mechanism (possibly via Culture Amp)
Risks | Mitigating Actions | Owner | Progress
In order to facilitate case management / tracking systems development or procurement is required. This is currently stalled. | Dedicated resource is needed to progress systems specification and project team to be formed. Timelines to be updated. | Kevin Colcough | This has been assessed as part of the overall requirements for the People and Culture function.
Reminder of Scope
Training and awareness for Managers and Staff on Once for Scotland policies Implementation of case review, lessons learned and case auditing processes Design and implementation of a case management system Design and implementation of regular process reporting / performance information Clarification and communication of the roles of the parties involved in people processes Design and implementation of any agreed changes to organisational model e.g. for investigations.
Milestone | Date | RAG
People Process Reporting fully in place | 31st December 2021 | Underway – but currently manual so time consuming
Early Resolution toolkit developed | 31st March 2022 (reforecast) | Working Group confirmed toolkit approach

## Slide 8
Wellbeing
Priority Status
Report Date: 9th March 2022
Green
Achieved in last quarter (Jan – March 22)
Proposal for additional Scottish Government funding evaluated – and alternative options now under review. Initial set of strategic themes for Wellbeing developed, and compared with good practice from other organisations and the feedback from the Listening and Learning Survey
Planned for next quarter (March - June 22)
Finalise plan for quick wins and use of additional Government funding and endowment funds Progress development of the longer term wellbeing strategy and priorities Plan communication, engagement and events around wellbeing
Risks | Mitigating Actions | Owner | Progress
There is a risk that the timeframe for progressing / deciding upon specific wellbeing activities is protracted and therefore misses the time colleagues most need additional support | Timely and regular workstream meetings combined with easy access to decision-making forum where needed (e.g. EDG) | Fiona Hogg | Options under development – will require rapid turnaround and decision-making to meet financial year end.
Reminder of Scope
Scope currently being finalised based upon working group and colleague feedback, but will include: Development of a long-term Wellbeing strategy, building upon the progress made on the support offer during the initial stages of the Covid pandemic Identification and implementation of ‘quick wins’ (or shorter term improvements) to support colleagues over the ongoing pandemic, including the allocation of additional Government funding
Milestone | Date | RAG
Wellbeing ‘quick wins’ / short term actions in place | 31st March 2022 | Ongoing engagement and input, final decisions expected by end Feb
Wellbeing Strategy developed and agreed | 31st May 2022 | Strategy input being analysed and solicited