## Open
RAG | Action Number | Meeting Date | Item | Action | Lead | Due Date | Status | Notes
Amber | 1 | 2021-03-28 | 12B Strategic Risk Register | The risks and opportunities associated with National Care Service to be included in future strategic risk registers and considered at a future development session. | Pam Cremin Fiona Davies Boyd Peters | 2022-12-01 | Partially Completed Considered at Board Briefing session 24 Jan 2023
Green | 2 | 2023-01-31 | 5 Chief Executive's Report - Maternity Services Business Case | Work to improve Maternity Services and address the significant workforce challenges had begun and progress had been made to ensure a balance between midwifery-led births and Community Midwifery Units. A full business case would return to the next meeting of the Board. | Katherine Sutton | 2023-05-30 | Complete | Update : The full business case is on the agenda for May 2023 meeting
Amber | 3 | 2023-03-28 | 5 IPQR - Radiology | Further information on Radiology outpatients/diagnostics trajectories would be brought back to the Board for discussion with respect to a delivery plan. | Boyd Peters Katherine Sutton |  |  | No due date was provided
Amber | 4 | 2023-03-28 | 8 Corporate Risk Register | Clearer representation of trajectory on Risk Register such as colour coding of risk levels or set out in order of higher to lower risks instead of subject headings | Rhiannon Boydell Boyd Peters | 2023-05-30
Green
Red

## Completed
RAG | Action Number | Meeting Date | Item | Action | Lead | Due Date | Status | Notes
Closed | Legacy | 2019-11-26 | 8. Highland Partnership Agreement | Agreed, that once the financial situation had been resolved, the Board would take a strategic look at the outcomes for integration, for North Highland and Argyll & Bute. | Chief Officers and Chief Executive | 2022-01-01 | Completed | Discussed with Louise Bussell & Fiona Davies Jan 2021 Integration Agreement signed off by both organisations in March 2021 and Scottish Government comments have now been incorporated. Formal approval from SG now awaited Consultation now underway on National Care Service
Closed | Legacy | 2021-01-26 | 6. Chief Executive’s Update | Learning from the experiences of the pandemic, and how to improve going forward. The Chief Executive intended to share the NHS Highland presentation with the Board at a future Board Development Session. | Chief Executive | 2022-03-01 | Completed | Remobilise, Recover, Redesign 1 Year Strategy agreed March 2021
Closed | Legacy | 2021-01-26 | 12. Public Bodies (Joint Working) (S) Act 2014 – Annual Performance Reports (a) Highland Health and Social Care Partnership | Approval had been received from the Scottish Government for the report to go to the March Health and Social Care Committee and be published at that point. It would be submitted to the next Board meeting. | Louise Bussell | 2021-03-30 | Completed
Closed | Legacy | 2021-01-26 | 13. Director of Public Health’s Annual Report 2020 | The Chair agreed to further discussion or a Development Session regarding inequalities as a result of Covid. | Chair |  | Completed | Now included in Plan for August Strategy Session
Closed | Legacy | 2021-03-30 | 8. The Culture Programme Update | Analysis on progress made in response to the Sturrock recommendations, a detailed action plan for the year ahead, longer term actions, and a detailed update on the Healing Process will be brought to the Board in May. | Fiona Hogg | 2021-05-01 | Completed | Culture Update to Board May 2021
Closed | Legacy | 2021-03-30 | 9. Implementation of National Whistleblowing Standards | Going forward there will be quarterly updates provided to the Board. | Fiona Hogg |  | Completed | Now included in Board Workplan
Closed | Legacy | 2021-03-30 | 14. Equalities Outcomes and Mainstreaming Report | The findings regarding social mitigation would be reported to the Board in May. | Tim Allison |  | Completed | Included on May Board agenda
Closed | Legacy | 2021-03-30 | 15. Naming of New Hospitals (b) Naming of the New Hospital for Skye, Lochalsh & Southwest Ross | The shortlist would be presented to the NHSH Board and the Project Programme Board for ratification. | Deborah Jones | 2021-06-01 | Completed | agreed in June 2021
Closed | Legacy | 2021-03-30 | 17. Committee Memberships Review | The proposals would be held in place until November when final Committee positions would be agreed. | Ruth Daly | 2022-01-01 | Completed | For January 2022 Board meeting
Closed | Legacy | 2021-05-25 | 9. NHS Highland Financial Plan | AGREED to hold a development session FRP Committee and Board members to hear greater detail about the changes in the approach to the budget. | Ruth Daly |  | Completed | Included in Plan for August Strategy Session
Closed | Legacy | 2021-05-25 | 17. Gaelic Language Plan Monitoring Report | AGREED to delegate authority to the Chair and the Chief Executive to approve the Gaelic Language Plan Monitoring Report to Bòrd na Gàidhlig in the due timescale and report back to the Board at the July meeting. | Ruth Daly | 2021-07-27 | Completed | Final agreed submission presented to the Board 27 July 2021 for noting
Closed | Legacy | 2021-07-27 | 8 IPQR | Further information around cancer services to be provided to the Board at a future meeting or a development session. | Katherine Sutton |  | Completed | Included on the Development Session forward plan 2021-22
Closed | Legacy | 2021-07-27 | 10. Board Risk Register | Inclusion of an indication of the direction of changes to show where improvements or deterioration had occurred | Boyd Peters |  | Completed | For consideration and inclusion in future iterations of the Strategic Risk Register
Closed | Legacy | 2021-09-28 | 10. Update on Healing Process | • Third organisational learning report to come to the Board, capturing a summary of participant feedback • Board Report on conclusion of the Healing Process in June 2022 | Fiona Hogg | 2022-07-01 | Completed | 2022-07-01
Closed | Legacy | 2021-09-28 | 12 a Risk Appetite and Risk Tolerance | Progress with developing the Board’s risk appetite and tolerance to be considered at a Board Development session | Boyd Peters | 2022-03-01 | Completed | Included in future plan for Development Sessions
Closed | Legacy | 2021-09-28 | 12 b Strategic Risk Register | The risks and opportunities associated with National Care Service to be included in future strategic risk registers and considered at a future development session. | Louise Bussell Fiona Davies Boyd Peters | 2021-12-01 |  | Included in future plan for Development Sessions
Closed | Legacy | 2021-09-28 | 14. NHS Highland Strategy Development | Final draft plan of NHS Highland Strategy to be presented at the May 2022 Board meeting | Lorraine Cowie | 2022-05-01 | Completed | Regular updates to be given at each board meeting.
Closed | Legacy | 2021-09-28 | 17. Board Assurance Framework | Improvement Plan to be a standing item on Board agendas throughout the pilot phase of assurance level reporting | Ruth Daly | 2021-11-01 | Completed | Regular updates to be given at each board meeting.
Closed | Legacy | 2021-11-30 | 19 Review of Board Governance Arrangements | Review pausing of development sessions in line with prioritising Board & Committee business. | Ruth Daly | 2022-03-01 | Completed | To be included in the March 2022 Board agenda
Closed | Legacy | 2022-01-25 | 11. Culture Programme Assurance Report | Detailed strategy for the Wellbeing workstream is expected to be ready for end of March 2022 | Fiona Hogg | 2022-05-01 | Completed | Due to be ready for end of March 2022, Deadline noted for May Board Meeting Update 29 March: detailed strategy for the wellbeing workstream will now be expected at the next meeting of the Board in May
Closed | Legacy | 2022-03-29 | 6. Chief Executive’s Report – Verbal Update of Emerging Issues | The Board agreed to extend the timeframe for consideration of the draft Strategy Report to July 2022. | Pamela Dudek | 2022-07-01 | Completed | Draft presented to 19 July 2022 development session, final version approved at 27 September 2022 Board.
Closed | Legacy | 2022-03-29 | 16. Review of Governance Light arrangements | The Board agreed to extend the current arrangements until the end of May 2022 which will be reviewed at the next Board Meeting (May) | Ruth Daly | 2022-05-01 | Completed
Closed | Legacy | 2022-03-29 | 17. Suspension of Standing Orders – Extension of Co-option onto NHS Highland Audit Committee | The Board agreed to: • Suspend Standing Order 9.7 relating to duration of the co-option arrangement and, • Extend the timeframe of the co-option arrangement for a period of two years with effect from 1 April 2022, subject to annual reviews. | Ruth Daly | 2024-04-01 | Completed
Closed | Legacy | 29/03/22 And 26/07/22 | 6. Chief Executive’s Report – Verbal Update of Emerging Issues | The Board agreed to extend the timeframe for consideration of the draft 5 year Strategy Report to July 2022. July Board extended this deadline to September | Pamela Dudek | 2022-09-01 |  | Update July 2022: See revised Chief Exec Update 26/07/22 – Draft Strategy will be taken to September Board Meeting
Closed | Legacy | 2022-05-31 | 6. Chief Executive’s Report – Verbal Update of Emerging Issues | H May to provide numbers of babies born en-route to hospital to the Board for assurance. | Heidi May | 2022-09-01 |  | Update Sept 2022: Update was received at Sept Board Meeting
Closed | Legacy | 2022-05-31 | 11. Finance Assurance Report Month 12 and NHS Highland Financial Plan 2022/23 | Financial related risks within the Risk Register to be reviewed | Heledd Cooper /Elaine Ward/ Lorraine Cowie | 2022-09-01 | Completed
Closed | Legacy | 2022-05-31 | 15. Strategic Risk Register | A revised Risk Register to be available for late Summer | Lorraine Cowie | 2022-09-01 | Completed
Closed | Legacy | 2022-05-31 | Health & Wellbeing Strategy | The Wellbeing Strategy will be included within the overall ADP/Together we Care Strategy with an update to the Board Meeting in November | Fiona Hogg/ Lorraine Cowie | 2022-11-01 | Completed
Closed | Legacy | 2022-07-26 | 5. Chief Executive’s Report – Verbal Update of Emerging Issues | The business case for Maternity Services will be brought to the September meeting of the Board. | Heidi May | 2022-09-01 | Completed
Closed | Legacy | 2022-07-26 | 5. Chief Executive’s Report – Verbal Update of Emerging Issues | The National Treatment Centre formal report on progress will come to the September meeting of the Board. | Deborah Jones | 2022-09-01 | Completed
Closed | Legacy | 2022-07-26 | 5. Chief Executive’s Report – Verbal Update of Emerging Issues | Draft strategy had been discussed at the Board Development Session in July and it was now anticipated that the Strategy would be brought to the Board for approval at its September meeting. | Lorraine Cowie | 2022-09-01 | Completed
Closed | Legacy | 2022-07-26 | 7. Integrated Performance and Quality Report | D Park provided apologies were given as some of the data around Falls and Infections as this had been corrupted. An update will be sent out prior to the next Board meeting. | David Park/ Lorraine Cowie | 2022-09-01 | Completed | Update provided to Sept Board Meeting
Closed | Legacy | 2022-11-29 | 7. Finance Assurance Report | The need for the Board to be fully briefed and updated on the budgetary challenges for adult social care. | Chief Officers | 2023-01-01 | Completed | Full update provided to the Board briefing session on 24 January 2023
Closed | Legacy | 2022-11-29 | 10. National Treatment Centre | D Jones agreed to provide numbers on how many staff will be recruited from Raigmore Hospital and other healthcare settings within NHS Highland out with the meeting. | Deborah Jones | 2023-01-01 | Completed | Information conveyed 16 December 2022
Closed | Legacy | 2022-11-29 | 12b People & Culture Strategic Risk Review | The Board APPROVED the interim updates to risk 877 as set out in Appendix 3 and AGREED that this risk should be included in the Corporate Risk Register with the Chief Executive as the Accountable officer. Oversight of the risk would be maintained by both the Highland Health and Social Care Committee, and Clinical Governance Committee for acute services, moving forward. | Fiona Hogg Boyd Peters Lorraine Cowie | 2023-01-01 | Completed | Risks have been added to the Corporate Risk Register
Closed | Legacy | 2023-01-31 | 5 Chief Executive’s Report – Verbal Update on Emerging Issues | Maternity Services Business Case • Work to improve Maternity Services and address the significant workforce challenges had begun and progress had been made to ensure a balance between midwifery-led births and Community Midwifery Units. A full business case would return to the next meeting of the Board. | Katherine Sutton | 2023-03-01 |  | Update : The full business case will come to the May 2023 meeting
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed
Closed